## Issues
Issue No. | Issue | Assign Date | Assign By | Estimated time (hour) | Start DateTime | End DateTime | Time
1 | Do not use New operator | 2021-04-06 | Maulik Modi | 1
2 | Avoid duplicate code | 2021-04-06 | Maulik Modi | 0.25
3 | Take Type Of Id as parameter | 2021-04-06 | Maulik Modi | 0.25
4 | Entities classes should be free from Attributes, remove reference from System.ComponentModel.DataAnnotations.Schema | 2021-04-06 | Maulik Modi | 2
5 | Update method should accept Id in path parameter | 2021-04-06 | Maulik Modi | 0.25
6 | Reference APi analyzer in API project | 2021-04-06 | Maulik Modi | 1
7 | Should document ApiResponseType | 2021-04-06 | Maulik Modi | 1